## Test summary report
Tester | TDHoang
Date | 2013-04-06
No | Function ID | Function name | Pass | Fail | Untested | Number of test cases
1 | 01 | Login as admin | 2 | 1 | 0 | 3
2 | 02 | Login as end user | 2 | 1 | 0 | 3

## Bug report
ID | Function name | Problem summary | How to reproduce it | Reported by | Date | Assigned to | Status | Comment
01 | Login as admin | Login with blank User name not display error | 1. Enter User Name : " " 2.Enter Password : "abcd" 3. Click "Ok" button | TDHoang | 2013-04-06 |  | Open
02 | Login as end user | Login with blank User name not display error | 1. Enter User Name : " " 2.Enter Password : "abcd" 3. Click "Ok" button | TDHoang | 2013-04-06 |  | Open